## GeneralModule
MODULE | MENU | PROGRAM | KETERANGAN MASALAH | STORE PROCEDURE / FUNCTION / VIEW | DEVELOPER |  | QC |  | Tgl Test | FIXING
[5 empty] | PIC | STATUS | PIC | STATUS |  | PIC | STATUS | COMMENT
General | Master - General | Organization |  |  | Syawal | Done | Ashadi | Done
|  | Company Profile |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Customer Class |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Supplier Class |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Customer Admin |  |  | Syawal | Done | BRY | Done | 2015-01-29
BRY
BRY
|  | Customer |  |  | Syawal | Done | BRY | Done | 2015-01-29
BRY
|  | Zip Code |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Reminder | 1. Reminder Date tidak bisa dipilih/ |  | Syawal | Done | BRY | X | 2015-01-26 |  |  | sudah sama seperti yang di desktop, untuk tanggal hanya aktif ketika memilih radio button hari raya
|  | Employee |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Employee Absence | Data Kosong |  | Syawal | Done | BRY | X | 2015-01-26 |  | Done | Silahkan coba kembali | 2015-02-05
|  | Tax |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Collector |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Document |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Document Sign |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Faktur Pajak Seq. |  |  | Syawal | Done | BRY | Done | 2015-01-29
|  | FPJ Signature Date |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Lookup |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Calendar |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Parameter |  |  | Syawal | Done | BRY | Done | 2015-01-26
|  | Approval |  |  | Syawal | Done | BRY | Done | 23/1/2015
|  | Message Boards |  |  | Syawal | Done
|  | Setting Security Report |  |  | Syawal | Done
| Master - Finance | Segment Chart of Account GL |  |  | Syawal | Done | BRY | Done | 2015-01-26
|  | Charf of Account GL |  |  | Syawal | Done | BRY | Done | 2015-01-29
|  | Period |  |  | Syawal | Done | BRY | Done | 2015-01-26
|  | Inquiry Credit Limit |  |  | Syawal | Done
| Utility | User |  |  | Syawal | Done | BRY | Done | 2015-01-26
|  | Change Password | 1. Tidak ada menunya |  | Syawal | Done | BRY | X | 2015-01-29 |  |  | menu di buat terpisah bukan di utylity on progress develop by osen
|  | Role |  |  | Syawal | Done | BRY | Done | 2015-01-26
|  | Menu |  |  | Syawal | Done
|  | Role Menu | 1. DI menu ini seharusnya terdapat "Sub Sub Module" contoh : Modul- Service, Sub Module-Transaction, Sub-Sub Module - Service, Menu Module - Input SPK |  | Syawal | Done | BRY | X | 2015-01-29 |  | Done | silahkan dicoba lagi | 2015-02-05
|  | Module |  |  | Syawal | Done
|  | Role Module |  |  | Syawal | Done | BRY | Done | 2015-01-29
|  | Auto No. Customer |  |  | Syawal | Done
|  | Auto No. Supplier |  |  | Syawal | Done
|  | Query Analyzer |  |  | Syawal | Done
|  | Pivot - Admin & Audit |  |  | Syawal | Done
|  | Language Setup |  |  | Syawal | Done
|  | Printer Setup |  |  | Syawal | Done
|  | Backup Database |  |  | Syawal | Done
|  | Backup Branch Data |  |  | Syawal | Done
|  | Upload Branch Data |  |  | Syawal | progress

## Pre-Sales-ITS
MODULE | MENU | PROGRAM | STORE PROCEDURE / FUNCTION / VIEW | DEVELOPER |  | QC |  | FIXING
|  |  |  | PIC | STATUS | PIC | STATUS | PIC | STATUS | COMMENT
Pre Sales / ITS | Master Prospect | Team Members
Outlets
Jabatan
Saleman Grade
Group Type Seq
Organization
| Inquiry Tracking System | Kartu Data Prospect
Input Indent System
| Inquiry | Inquiry Follow Up
Inquiry Summary
Analisa Lost Case
Sales Achievement
SIS History
Inquiry Outstanding Prospect
Inquiry by Period
Inquiry ITS
Inquiry ITS (Management)
Inquiry ITS with Status
Inquiry Indent
| Utility | Generate KDP
Upload File
Utility KDP
Transfer KDP

## Sales
MODULE |  | PROGRAM | KETERANGAN | STORE PROCEDURE / FUNCTION / VIEW | DEVELOPER |  | QC |  | Tgl Test | FIXING
[5 empty] | PIC | STATUS | PIC | STATUS |  | PIC | STATUS | COMMENT
Sales | Master | Reference |  | sp_RefferenceTypeLookup | Rijal | Done | Azzhari | Done | 2015-01-26
|  | Model |  |  | Rijal | Done | Azzhari | Done | 2015-01-26
|  | Model Color |  | sp_omMstModelColour, omMstModelColourView | Rijal | Done | Azzhari | Done | 2015-01-26
|  | Model Year |  | sp_omMstModelYear | Rijal | Done | Azzhari | Done | 2015-01-26
|  | Perlengkapan |  |  | Rijal | Done | Azzhari | Done | 2015-01-26
|  | Model Perlengkapan |  | omMstModelPerlengkapanView | Rijal | Done | Azzhari | Done | 2015-01-26
|  | Karoseri |  | sp_KaroseriBrowse | Rijal | Done | Azzhari | Done | 2015-01-26
|  | Price List Beli |  | sp_MstPriceListBeliBrowse | Rijal | Done | Azzhari | Done | 2015-01-26
|  | Price List Jual |  | sp_MstPriceListJualBrowse | Rijal | Done | Azzhari | Done | 2015-01-26
|  | BBM & KIR |  | sp_BBNKIRBrowse | Rijal | Done | Azzhari | Done | 2015-01-26
|  | Model Account |  | sp_MstModelAccountBrowse | Rijal | Done | Azzhari | Done | 2015-01-26
|  | Company Account |  |  | Rijal | Done | Azzhari | Done | 2015-01-27
|  | Sales Target |  |  | Rijal | Done | Azzhari | Done | 2015-01-27
|  | Master Others Inventory |  | sp_MstOthersInventoryBrowse | Rijal | Done
| Purchase | Purchase Order | perhitungan DiscExcludePPn nilai di tabel omTrPurchasePOModel tidak sesuai, contoh PONo = 'PUR/15/000064' ---- (Done) |  | David | Done | Dimas | Done | 2015-01-27
|  | Bukti Penerimaan Unit |  | OmTrPurchaseBPUView | Rudi | Done
|  |  | BPU - SJ tidak bisa "add" detail nomor rangka ---- (Done) | OmTrPurchaseBPULookupView |  |  | Dimas | Done | 2015-01-27
|  |  | Tidak bisa Approve BPU - SJ ---- (Done) | OmTrPurchaseBPUDetailView |  |  |  |  | 2015-01-27
OmSelectReffSJTrueView
OmSelectReffSJFalseView
OmSelectReffSJBookingView
OmSelectReffNoView
|  | BPU Attribute |  |  | Syawal | Done
|  | HPP | Tidak bisa save muncul error "connection to the server failed" |  | Syawal | Done | Dimas | X | 2015-01-27
|  |  | data tidak update ke OmMstVehicle |  |  |  |  | X | 2015-01-29
|  |  | browse data kosong |  |  |  | Dimas | Done | 2015-01-29
|  | Purchase Return |  |  | Rijal | Done
|  | Perlengkapan In |  |  | David | Done
|  | Perlengkapan Adjustment |  |  | Rijal | Done
|  | Karoseri |  |  | Syawal | Done
|  | Karoseri Terima |  |  | Rijal | Done
| Sales | Draft Sales Order |  |  | Rudi | on progress
|  | Sales Order |  |  | Syawal | on progress
|  | Delivery Order (DO) |  |  | Yanuar | Done
|  | BPK |  |  | Yanuar | Done
|  | Perlengkapan Out |  |  | Yanuar | Done
|  | Invoice |  |  | Yanuar | on progress
|  | Return |  |  | Yanuar | on progress
|  | Permohonan Faktur Polisi |  |  | Rijal | Done
|  | Faktur Polisi |  |  | Rudina | Done
|  | Permohonan Faktur Polisi (Sub-Dealer) |  |  | David | Done
|  | Maitenance Permohonan Faktur Polisi |  |  | Rijal | Done
Kwitansi Unit
|  | SPK & Tracking BBN |  |  | Syawal | Done
|  | Tanda Terima BPKB |  |  | Rijal | Done
|  | Tanda Terima STNK |  |  | Rijal | Done
| Inventory | Transfer Out | Tidak bisa Print |  | Syawal | Done | Dimas | X | 2015-01-29
|  |  | belum ada validasi cek nilai HPP = 0 |  |  |  |  | X
|  |  | approve tidak merubah status, TransferOutNo, LastUpdateBy, LastUpdateDate di OmMstVehicle |  |  |  |  | X
|  | Transfer In | centang "Pilih Semua" tidak otomatis add detil transfer in |  | Syawal | Done | Dimas | X | 2015-01-29
|  |  | Layout detil transfer in tidak sama dengan versi desktop (tidak ada pilihan SalesModelYear) |  |  |  |  | X
|  | Ganti Warna |  |  | Syawal | Done
Transfer In Multi Branch
Transfer Out Mult Branch
| Stock Opname/Taking | Proses Stock Taking |  |  | Rudi | Done
|  | Entry Inventory Tag |  |  | Rudi | Done
|  | Posting Stock Taking |  |  | Rudi | Done
|  | Inventory Tag |  |  | Rudi | Done
|  | Stock Opname Kendaraan |  |  | Rudi | Done
|  | Daftar Rincian Kendaraan yang Hilang |  |  | Rudi | Done
| Inquiry - Purchase | Purchase Order |  | sp_InquiryPurchaseOrder | Rijal | Done
|  | BPU Attribute |  | sp_InquiryBPU | Rijal | Done
|  | HPP |  | sp_InquiryHPP | Rijal | Done
|  | Purchase Return |  | sp_InquiryPurchaseReturn | Rijal | Done
|  | Perlengkapan In |  | sp_InquiryPerlengkapanIn | Rijal | Done
|  | Perlengkapan Adjustment |  | sp_InquiryPerlengkapanAdjustent | Rijal | Done
|  | Karoseri |  | sp_InquiryKaroseri | Rijal | Done
|  | Karoseri Terima |  | sp_InquiryKaroseriTerima | Rijal | Done
| Inquiry - Sales | Sales Order |  | sp_InquirySalesOrder | Rijal | Done
|  | Delivery Order |  | sp_InquiryDeliveryOrder, sp_InquiryDeliveryOrderDetail | Rijal | Done
|  | BPK |  | sp_InquiryBPK, sp_InquiryBPKDetail | Rijal | Done
|  | Invoice |  | sp_InquiryInvoice, sp_InquiryDebetNote | Rijal | Done
|  | Return |  | sp_InquirySalesReturn, sp_InquirySalesReturnDetailModel | Rijal | Done
|  | Perlengkapan Out |  | sp_InquiryPerlengkapanOut | Rijal | Done
|  | Permohonan Faktur Polisi |  | sp_InquirySalesReq | Rijal | Done
|  | SPK & Tracking BBN |  | sp_InquirySPK | Rijal | Done
| Inquiry - Inventory | Transfer Out |  | sp_InquiryTransferOut, sp_InquiryTransferOutDetail | Rijal | Done
|  | Transfer In |  | sp_InquiryTransferIn, sp_InquiryTransferInDetail | Rijal | Done
|  | Stock Kendaraan |  | sp_InquiryStokKendaraan | Rijal | Done
|  | Stock Perlengkapan |  | sp_InquiryStokPerlengkapan | Rijal | Done
|  | Data Kendaraan |  | sp_InquirDataKendaraan, sp_InquirDetailDataKendaraan | Rijal | Done
|  | Data Kendaraan (tanpa COGS) |  |  | Rijal | Done
Data DCS (Sales)
Sales
Customer
Productivity Sales Force
| Laporan - Master | Reference |  | usprpt_OmRpMst001 | Rijal | Done
|  | Model |  | usprpt_OmRpMst002 | Rijal | Done
|  | Model Color |  | usprpt_OmRpMst003 | Rijal | Done
|  | Model Year |  | usprpt_OmRpMst004 | Rijal | Done
|  | Perlengkapan |  | usprpt_OmRpMst005 | Rijal | Done
|  | Model Perlengkapan |  | usprpt_OmRpMst006 | Rijal | Done
|  | Karoseri |  | usprpt_OmRpMst007 | Rijal | Done
|  | Price List Beli |  | usprpt_OmRpMst008 | Rijal | Done
|  | Price List Jual |  | usprpt_OmRpMst009 | Rijal | Done
|  | BBN & KIR |  | usprpt_OmRpMst010 | Rijal | Done
|  | Model Account |  | usprpt_OmRpMst011 | Rijal | Done
| Laporan - Purchase | Purchase Order |  |  | Syawal | Done
|  | BPU |  |  | Syawal | Done
|  | HPP |  |  | Syawal | Done
|  | Perlengkapan In |  |  | Syawal | Done
|  | Perlengkapan Adjustment |  |  | Syawal | Done
|  | Register Pesanan Kendaraan |  |  | Syawal | Done
|  | Register Bukti Penerimaan Unit |  |  | Syawal | Done
|  | SDMS-INV DO Attributes |  |  | Syawal | Done
|  | Register Pengembalian Unit |  |  | Syawal | Done
|  | Laporan Statistik Pembelian |  |  | Syawal | Done
|  | Register SPK Karoseri |  |  | Syawal | Done
|  | Register Penerimaan Karoseri |  |  | Syawal | Done
| Laporan - Sales | Sales Order |  |  | Rijal | Done
|  | Delivery Order |  |  | Rijal | Done
|  | BPK |  |  | Rijal | Done
|  | Invoice |  |  | Rijal | Done
|  | Sales Achievement Record |  |  | Rijal | Done
|  | Register Sales Order |  |  | Rijal | Done
|  | Register Delivery Order |  |  | Rijal | Done
|  | Register Bukti Pengiriman Kendaraan |  |  | Rijal | Done
|  | Register Faktur Penjualan Unit |  |  | Rijal | Done
|  | Register Retur Invoice |  |  | Rijal | Done
|  | Register Pembatalan Sales Order |  |  | Rijal | Done
|  | Register Nota Debet |  |  | Rijal | Done
|  | Register Pelanggan Per Leasing |  |  | Rijal | Done
|  | Daftar Rincian Kendaraan Bermotor |  |  | Rijal | Done
Laporan Faktur Penjualan (Pre-Printed)
|  | Laporan Penjualan Terbaik |  |  | Firman | on progress
|  | Laporan Faktur-faktur Request yang sudah di Generate |  |  | Firman | on progress
|  | Summary Permohonan Faktur Polisi |  |  | Firman | on progress
|  | Rekapitulasi Harian |  |  | Firman | on progress
|  | Register Faktur Polisi |  |  | Rijal | Done
|  | Register Harian Penerbitan Faktur Polisi |  |  | Rijal | Done
|  | Oustanding Blangko Faktur Polisi |  |  | Syawal | Done
|  | Register SPK |  |  | Syawal | Done
|  | Laporan Faktur |  |  | Syawal | Done
|  | Laporan Penggunaan Blangko |  |  | Syawal | Done
|  | Customer List - Sales Unit |  |  | Syawal | Done
Tanda Terima BPKB
|  | Daftar BPKB |  |  | Syawal | Done
Daftar BPKB Per Lokasi
Laporan Outstanding SPK
Tanda Terima Faktur / Pengajuan Pengurusan BBN
Laporan Daily Sales All Branch
Laporan Daily Sales All Branch V.2
Laporan Data Customer Profile
| Laporan - Inventory | Perincian Stock |  |  | David | Done
|  | Stock Inventory |  |  | David | Done
Stock Inventory V.2
|  | Laporan Stock Kendaraan |  |  | David | Done
|  | Transfer Kendaraan In |  |  | David | Done
Transfer Kendaraan In Multi Branch
|  | Transfer Kendaraan Out |  |  | David | Done
Transfer Kendaraan Out Multi Branch
|  | Ganti Warna |  |  | David | Done
|  | Dealer Stock |  |  | David | Done
| Laporan | Dokumen Pending |  |  | Syawal | Done
|  | Statistik Salesman |  |  | Syawal | Done
|  | Laporan Laba Rugi |  |  | Syawal | Done
Laporan Laba Rugi V.2
Sales Report with Vehicle Ownership Info
| Utility | Upload File
Send File
Posting Journal
Re-Posting Journal
Tutup Bulan
Upload From DCS
Upload Data Dealer (Sales)
Download Master Model Suzuki

## Sparepart
MODULE | MENU | PROGRAM | STORE PROCEDURE / FUNCTION / VIEW | KETERANGAN | DEVELOPER |  | QC |  |  | FIXING
[5 empty] | PIC | STATUS | PIC | STATUS | TANGGAL TEST | PIC | STATUS | COMMENT
Spare Part | Master | Master Item | SpMasterItemView,SpMasteritemStockAlokasiView | Saat Pembuatan Item part, di cek di Tabel SpMstItems, kolom OnHand dan kawan kawan nya terisi "Null" | Sanudin | Done | Bry | X | 2015-01-29 | Rudi | Done
|  | Item Lokasi | SpMstItemLocView,SpMstItemLocItemLookupView |  | Sanudin | Done | Bry | Done | 2015-01-29
|  | Item Modifikasi (Substitution Part) | sp_SpMstItemModifInfo,sp_SpMstItemModifSelect,sp_SpMstItemcondition |  | Sanudin | Done | Bry | Done | 2015-01-29
|  | Item Price | sp_SpItemPriceView | Part Baru tidak ditemukan, padahal di Items dan Item loc Active | Sanudin | Done | Bry | X | 2015-01-29 | Rudi | Done
|  | Part Campaign untuk Pembelian | sp_spMstPurchCampaignView |  | Sanudin | Done | Bry | Done | 2015-01-29
|  | Part Campaign untuk Penjualan | sp_spMstSalesCampaignView |  | Sanudin | Done | Bry | Done | 2015-01-29
|  | Moving Code | sp_spMstMovingCodeView |  | Sanudin | Done | Bry | Done | 2015-01-29
|  | GL Account Mapping | sp_spMstAccountView,sp_spgnMstAccountView |  | Sanudin | Done | Bry | Done | 2015-01-29
|  | Parameter Order | sp_spMstOrderParamView,sp_spMstOrderParamLookup |  | Sanudin | Done | Bry | Done | 2015-01-29
|  | Target Penjualan | sp_spMstSalesTargetview,sp_spCategoryCodeview |  | Sanudin | Done | Bry | Done | 2015-01-29
|  | Item Konversi | sp_SpMstItemConversionview |  | Sanudin | Done | Bry | Done | 2015-01-29
|  | Master Company Account | sp_spMstCompanyAccount,sp_spgnMstAccountView |  | Sanudin | Done | Bry | Done | 2015-01-29
| Pembelian | Proses Suggestion Order |  |  | David | Done | DHT |  | 2015-01-26
|  | Entry Pesanan Sparepart | uspfn_spMasterPartView,uspfn_SpOrderSparepartView,uspfn_spSuppliers |  | Sanudin | Done | Bry | Done | 2015-01-29
|  | Maintenance On Order Substitusi | uspfn_SpposView,uspfn_SppartView |  | Sanudin/Rudi | Done | Bry | Done | 2015-01-29
|  | Maintenance On Order PO | uspfn_SpposView,uspfn_SppartView |  | Sanudin/Rudi | Done | Bry | Done | 2015-01-29
| Penerimaan | Entry Draft Penerimaan (Binning) | SpEdpSupplier,sp_EdpPelangganBrowse, SpEdpDnNo, sp_EdpTransNo, sp_EdpDocNoBrowse, sp_EdpBpsNoBrowse, SpEdpPartNo, SpEdpPartNo_Pembelian, SpEdpPartNo_Internal, SpEdpPartNo_Others, SpEdpDetail, SpSelectByNoWRS, SpSelectByNoBinning |  | Fery | Done | Bry | Done | 2015-01-29
|  | Entry Penerimaan Persediaan (WRS) | SpGridEntryWRS |  | Fery | Done | Bry | Done | 2015-01-29
|  | Entry HPP | sp_EntryHPPBrowse, SpWRSHpp, SpLoadEntryHPP |  | Fery | Done | Bry | Done | 2015-01-29
|  | Entry Claim Supplier | SpGridPartNo, uspfn_SpWrongPart, SpPartNoView, SpWRSNo, SpEntryCS | setelah Isi WRS, tidak ada Tombol Save nya | Fery | Done | Bry | X | 2015-01-29 | Rudi | Done
|  | Receiving Claim Vendor | SpVendorClaimView, sp_SpReceiveClaimNo, SpPartOrderView |  | Fery | Done | Bry | X | 2015-01-29 |  |  | Tidak ada keterangan bug-nya
| Pengeluaran | Entry Pengeluaran Stock |  | 1. Di Klik Tombol Customer, tidak ada datanya | David | Done | Bry | X | 2015-01-29 | David | Done
|  |  |  | 2. Saat buat baru Customer, di teropong Customer dan di Search, data tidak ada, seakan2 Data Customer tidak nyambun ke menu ini. |  |  | Bry | X | 2015-01-29 | David | Done
|  |  |  | 3. Saar proses Stok Alokasi, Muncul Error dan setelah di OK, dan di coba lagi Klik Stok Alokasi, muncul peringatan Nomor Dokumen Sudah Terposting, dan dokumen Hilang |  |  | Bry | X | 2015-01-29 | David | Done
|  | Pembuatan PL & Entry Picked Qty PL |  | 1. Transaksi SO dilakukan di Aplikasi Desktop karena dari SDMS WEB tidak bisa, saat ingin Picking di SDMSWEB, data tidak ada, dan akan muncul jika Data Profit Center Customer adalah "General" | Albai | Done | Bry | X | 2015-01-29 | Rudi | Done
|  |  |  | 2. Saat ingin Generate PL, ada peringatan Credit Limit di Customer harus diisi, semestinya tidak usah, dan juga Kolom Discont jg harus diisi, apalagi ini, lebih ga perlu. |  |  | Bry | X | 2015-01-29 | Rudi | Done
|  | Pembuatan Faktur Penjualan | uspfn_SPGetSpTranDetails, uspfn_getCustSPTrans, uspfn_spGetFPJLookUp, uspfn_spGetPickingList | 1. Proses SO dan Picking List dilakukan di Desktop, tetapi proses Faktur Penjualan di Proses di SDMS WEB, saat ingin di Save, muncul Error, LockingDate di Profit Canter tidak boleh "Null" | Albai | Done | Bry | X | 2015-01-29 | Rudi | Done
|  | Pembuatan Lampiran Dokumen Non Penjualan | uspfn_spGetLookupLMP4Srv, uspfn_spGetLookupLMP, uspfn_spGetSpTrnSBPSFDtl, uspfn_spGetSpTrnSLmpDtl |  | Albai | Done
|  | Pemeliharaan Faktur Penjualan | uspfn_spGetSpTrnSFPJHdr, uspfn_GetCustomerByProfitCenterCodeId, uspfn_spGetSpTrnSFPJDtl |  | Albai | Done
|  | Lampiran Dokumen Service | uspfn_GenerateSSPickingslip, uspfn_GenerateBPSLampiran, uspfn_spSelectPickingSlip, uspfn_SelectJobOrderNo4SOServiceEnhanche |  | Albai | Done
Entry Return Penjualan
|  | Entry Return Supply Slip | uspfn_GetReturnSupplySlip, uspfn_GetReturnSSDetails, uspfn_GetSPKNoService, uspfn_GetMaxQtyReturSupplySlip, uspfn_spGetNoLampiranReturSupplySlip |  | Albai | Done
Pembatalan Outstanding BO
Pembatalan Outstanding BO Keseluruhan
|  | Entry Return Service |  |  | David | Done
| Persediaan | Inventory Adjustment | uspfn_spTrnIAdjustDtlview |  | David | Done
|  | Warehouse Transfer | uspfn_spTrnIWHTrfDtlview |  | David | Done
|  | Reserved Sparepart | uspfn_spTrnIReservedDtlview,uspfn_spMasterPartView |  | David | Done
| Stock Opname | Proses Inventory Form / Tag | sp_SpSOSelectforInsert |  | Yanuar | Done
|  | Proses Blank Inventory Form / Tag |  |  | Yanuar | Done
|  | Entry Inventory Form / Tag | sp_SpSOSelectforLookup,sp_SpSOSelectforEntry |  | Yanuar | Done
|  | Pembatalan Blank Inventory Form / Tag |  |  | Yanuar | Done
|  | Cetak Analisa Stock Taking | sp_IsValidSTAnalyze |  | Fery | Done
|  | Posting Data Stock Taking to Master |  |  | Fery | Done
| Tutup Periode | Proses Tutup Bulan | sp_CheckValidTrans, sp_UpdateBORegisterTuning, InsertHistoryItemStatusTuning, sp_UpdateDemandAverageTuning, sp_UpdateABCClassTuning, sp_UpdateMovingCodeTuningV2, sp_InsertHistoryMovementTuning, sp_UpdateBOMTuning, sp_UpdateOrderPointTuning, sp_InsertTransactionHistoryTuning, sp_UpdateDemandHistoryTuning |  | Fery | Done
| Inquiry | Inquiry Data Pemasok | uspfn_spSuppliers |  |  | Done
|  | Inquiry Data Pelanggan |  |  |  | Done
|  | Inquiry Item Sparepart | uspfn_sp_partinquiry,uspfn_sp_partinquiry_location,uspfn_sp_partinquiry_onorder |  |  | Done
|  | Inquiry Item Sparepart (HQ) | uspfn_sp_partinquiry_subsitusi, uspfn_sp_partinquiry_demandandsales |  |  | Done
|  | Inquiry Item Sparepart (Simple) | uspfn_sp_partinquiry_demandandsaleshq, uspfn_spModelGridLookup |  |  | Done
|  | Inquiry Penerimaan Barang | uspfn_GetInqReceivingHdr, uspfn_sp_inquiry_penerimaan_barang_detail |  |  | Done
|  | Inquiry Sales Order | uspfn_sp_inquiry_sales_order, uspfn_sp_inquiry_sales_order_detail |  |  | Done
|  | Inquiry Supply Slip | uspfn_sp_inquiry_supply_slip, *_sum, *_detail, *_detail_sum |  |  | Done
|  | Inquiry Data DCS (Sparepart) |  |  |  | on progress
|  | Inquiry Sparepart |  |  |  | on progress
Inquiry Part Sales
| Utility | Upload File |  |  | Sanudin | Preparing
|  | Switch Type Part User |  |  | Yanuar | Done
|  | Send File |  |  | Sanudin | Preparing
|  | Reset Stock Opname |  |  | Yanuar | Done
|  | Upload from DCS |  |  | Sanudin | Preparing
|  | Maintain Harga Pokok | sp_MaintainAvgCostItem |  | Fery | Done
|  | Maintain Type Part |  |  | Fery | Done
|  | Upload Data Dealer (sparepart) |  |  | Sanudin | Preparing
| Report - Master | Daftar Master Sparepart |  |  | Yanuar | Done
|  | List Master Substitusi |  |  | Yanuar | Done
|  | Daftar Perubahan Outstanding Pesanan |  |  | Yanuar | Done
| Report - Pembelian | Suggestion Order |  |  | Yanuar | Done
|  | Daftar Pesanan Sparepart | sp_SpPosLkp |  | Yanuar | Done
|  | Daftar On Order Per Part |  |  | Yanuar | Done
| Report - Receiving | Binning List Pembelian | RptBinningBrowse |  | Fery | Done
|  | WRS Pembelian | RptWRSBrowse |  | Fery | Done
|  | Entry HPP | RptHPPBrowse |  | Fery | Done
|  | Claim Vendor Form | RptClaimNo |  | Fery | Done
|  | Receiving Claim Vendor Form | RptClaimReceivedNo |  | Fery | Done
| Report - Inventory | Inventory Adjustment | RptAdjustmentNoBrowse |  | Fery | Done
|  | Warehouse Transfer | RptWarehouseTransferBrowse |  | Fery | Done
|  | Reserved Sparepart | RptReservedBrowse |  | Fery | Done
| Report - Penjualan | Daftar Picking List |  |  | Yanuar | Done
|  | Daftar Pengeluaran Stock |  |  | Yanuar | Done
|  | Daftar Faktur Penjualan |  |  | Yanuar | Done
|  | Daftar Lampiran Dokumen Non Penjualan | sp_SpSrvLampLkp |  | Yanuar | Done
Daftar Lampiran Faktur Penjualan
|  | Daftar Sales Retur Memo |  |  | Yanuar | Done
Daftar Cancel Faktur Service
|  | Daftar Slip Supply Retur Memo |  |  | Yanuar | Done
|  | Daftar Outstanding Supply Slip |  |  | Yanuar | Done
|  | Daftar Back Order Bulanan Per Langganan |  |  | Yanuar | Done
|  | Daftar Back Order Harian Per Part |  |  | Fery | Done
|  | Daftar Back Order Harian Per Langganan |  |  | Fery | Done
|  | Daftar Back Order Cancel |  |  | Fery | Done
Daftar Faktur Penjualan (Pre-Printed)
| Report - Posting | Analisa Sparepart Menurut ABC Class | usprpt_SpRpTrn017 AnalisaSPMnrtABCclass.js |  | Syawal | Done
|  | Analisa Sparepart Menurut Moving Code | usprpt_SpRpTrn018 AnalisaSPMnrtMvngCode.js |  | Syawal | Done
|  | Mutasi Stock Bulanan | usprpt_SpRpTrn019 MutasiStockBulanan.js |  | Syawal | Done
| Report - Stock Taking | Inventory Stock Taking Tag | usprpt_SpRpTrn020 InvStockTakingTag.js |  | Syawal | Done
|  | Inventory Stock Taking Form | usprpt_SpRpTrn021 InvStockTakingForm,js |  | Syawal | Done
|  | Analisa Stock Taking | usprpt_SpRpTrn022 AnalisaStockTaking.js |  | Syawal | Done
|  | Daftar Inventory Form / Tag | usprpt_SpRpTrn023 DaftarInvFT.js |  | Syawal | Done
|  | Daftar Outstanding Inventory Form / Tag | usprpt_SpRpTrn024 DaftarOutInvFT.js |  | Syawal | Done
|  | Daftar Transaksi Stock Taking Harian | usprpt_SpRpTrn025 DaftarTrxStockTakingHarian.js |  | Syawal | Done
| Report - Reports | Kartu Stock | usprpt_SpRpSum001 |  | Rudi | Done
|  | Daftar Item dengan Penjualan Terbaik | usprpt_SpRpSum002 |  | Rudi | Done
|  | Daftar Analisa Service Ratio Per Pelanggan | usprpt_SpRpSum003 DftAnalisaServiceRatioPelanggan.js |  | Syawal | Done
|  | Daftar Part Per MC, ABC Class & Demand | usprpt_SpRpTrn040 DftPartPerMCABCclassDemand.js |  | Syawal | Done
|  | Daftar Ringkasan Service Ratio | usprpt_SpRpSum004 DftRingkasanServiceRatio.js |  | Syawal | Done
|  | Daftar Penjualan Per Pelanggan | usprpt_SpRpSum005 DftPenjualanPerPelanggan.js |  | Syawal | Done
|  | Daftar Barang yang Dipinjam | usprpt_SpRpSum006 DftBarangPinjam.js |  | Syawal | Done
|  | Daftar Barang yang harus Dikembalikan | usprpt_SpRpSum007 DftBarangKembali.js |  | Syawal | Done
|  | Daftar Perubahan Harga Potongan, Beli & Jual | usprpt_SpRpSum008 DftPerubahanHrgPotonganBeliJual.js |  | Syawal | Done
|  | Daftar Perubahan Average Cost | usprpt_SpRpSum009 DftPerubahanAverageCost.js |  | Syawal | Done
|  | Daftar Pajak Keluaran | usprpt_SpRpSum010 DftPajakKeluaran.js |  | Syawal | Done
|  | Daftar Part Per Nomor Part | usprpt_SpRpSum011 DftPartPerNoPart.js |  | Syawal | Done
|  | Stock Information | usprpt_SpRpTrn042 StockInformation.js |  | Syawal | Done
|  | Lampiran Faktur untuk Supply Slip & Unit | usprpt_SpRpSum012 FakturSupplySlipUnit.js |  | Syawal | Done
|  | Laporan Penjualan Per Class, Area & Lokasi | usprpt_SpRpSum013 PenjualanClassAreaLokasi.js |  | Syawal | Done
|  | Laporan Aktivitas Transaksi | usprpt_SpRpSum014 AktifitasTrx.js |  | Syawal | Done
|  | Daftar Over Stock | usprpt_SpRpSum015 DftOverStock.js |  | Syawal | Done
|  | Laporan Laba Rugi | usprpt_SpRpSum019A LabaRugi.js |  | Syawal | Done
|  | Laporan Rekapitulasi Omzet | usprpt_SpRpSum020 RekapitulasiOmzet.js |  | Syawal | Done
| Report - Register | Supply Slip |  |  | David | Done
|  | Supply Slip Outstanding |  |  | David | Done
|  | History Supply Slip Outstanding |  |  | David | Done
|  | Register Lampiran Faktur Non Penjualan |  |  | David | Done
|  | Register Bon Pengeluaran Sparepart |  |  | David | Done
|  | Register Bon Pengeluaran Sparepart Outstanding |  |  | David | Done
|  | Register Penjualan (Tunai & Kredit) |  |  | David | Done
|  | Register Penjualan Per Pelanggan (Tunai & Kredit) |  |  | David | Done
|  | Register Penjualan |  |  | David | Done
|  | Register Faktur Penjualan (HQ) |  |  | David | Done
|  | Register Retur Penjualan |  |  | David | Done
|  | Register Retur Supply Slip |  |  | David | Done
|  | Register Faktur Penjualan Per Pelanggan (HQ) | uspfn_spCustRptRgs |  | David | Done
|  | Register Detail Retur Penjualan | uspfn_spCustRptRgs |  | David | Done
|  | Register Claim Form |  |  | David | Done
|  | Register Claim Cancel |  |  | David | Done
|  | Daftar Outstanding Claim |  |  | David | Done
|  | Register Pesanan Sparepart |  |  | David | Done
|  | Register Penerimaan Pembelian |  |  | David | Done
|  | Register Warehouse Receiving Sheet |  |  | David | Done
|  | Register HPP Sparepart |  |  | David | Done
|  | Register Inventory Adjustment |  |  | David | Done
|  | Register Warehouse Transfer |  |  | David | Done
|  | Daftar Dokumen Pending |  |  | David | Done
|  | Report untuk Kantor Pajak |  |  | David | Done
|  | Pelanggan Overlimit |  |  | David | Done
|  | Register Rekon Sparepart |  |  | David | Done
|  | Register Perubahan Average Cost |  |  | David | Done

## Service
MODULE | MENU | PROGRAM | KETERANGAN | STORE PROCEDURE / FUNCTION / VIEW | DEVELOPER |  | QC |  | Tgl Test | FIXING
[5 empty] | PIC | STATUS | PIC | STATUS |  | PIC | STATUS | COMMENT
Service | Master | Reference Service |  | SvReffServiceView | Fery | Done | eko | done | 2015-01-27
|  | Tipe Pembayaran | 1. tidak bisa edit/ganti data pelanggan | SvBillTypeView | Fery | Done | eko | x | 2015-01-27 | Rudi | Done
SvGetCustomerDetailView
|  | Stall |  | SvStallView | Fery | Done | eko | done | 2015-01-27
|  | Waktu Kerja |  | SvWaktuKerja | Fery | Done | eko | done | 2015-01-27
|  | Kehadiran Mekanik |  | SvMechanicAvbView | Fery | Done | eko | done | 2015-01-27
SvGetMekanik
|  | Garansi |  | SvGaransiView | Fery | Done | eko | done | 2015-01-27
SvBMView
SvJTView
|  | Campaign |  | SvCampaignView | Fery | Done | eko | done | 2015-01-27
SvComplainView
SvDefectView
SvOperationView
|  | Pekerjaan | 1. Tidak bisa di Browse | SvPekerjaanView | Fery | Done | Bry |  | 2015-01-26 |  | Done
SvBasicModelPekerjaan
SvJobView
SvGroupJobView
SvNomorAccView
SvRincinJob
SvRincianBrowser
SvRincianPart
SvPartNoView
SvBasicCopy
uspfn_CopyBasicModel(sp)
|  | Tarif Kupon Service Gratis (KSG) |  | SvKSGView | Fery | Done | eko | done | 2015-01-27
SvBasicKsgView
|  | Tarif Jasa |  | SvTarifJasaView | Fery | Done | eko | done | 2015-01-27
SvLaborCode
|  | Kendaraan & Pelanggan | 1. tombol save, edit tidak muncul | SvKendaraanPel | Fery | Done | eko | x | 2015-01-27 |  | Done
SvChassicView
SvCBasmodView
SvColorView
SvCustomerDetailView
SvGetTableChassis
SvMstDealerView
|  | Kontrak Service |  | SvKontrakServiceView | Fery | Done | Ara |  | 2015-01-28
SvCustomerDetailView
SvVehicleDetailView
|  | Klub |  | SvNoPolisi | Fery | Done | Ara |  | 2015-01-28
SvClubView
SvClubTable
|  | Event |  | SvEventView | Fery | Done | Ara |  | 2015-01-28
SvJobView
SvCBasmodView
|  | Paket Service |  |  | Fery | Done | Ara |  | 2015-01-28
|  | Pendaftaran Paket Service |  |  | Fery | Done | Ara |  | 2015-01-28
|  | Target |  |  | Fery | Done | Ara |  | 2015-01-28
|  | Account |  |  | Fery | Done | eko | done | 2015-01-27
|  | Pendaftaran Campaign |  |  | Fery | Done
| Transaksi - Perawatan Kendaraan | Input SPK (Admin) | 1. Saat Save input SPK, No Dokumen SPK tidak langsung keluar | uspfn_SvTrnJobOrderOpen | Yanuar | Done | Bry |  | 2015-01-26
|  |  | 2. Kolom PPN tidak harus ada, karna sudah terformat di Master Customer/Pelanggan | uspfn_SvTrnJobOrderClose
uspfn_SvTrnJobOrderCancel
uspfn_SvTrnJobOrderCreate
uspfn_SvTrnServiceDeleteDtl
uspfn_SvTrnServiceSaveDtl
uspfn_GnDocumentGetNew
uspfn_SvTrnServiceSelectDtl
uspfn_SvTrnInvoiceDraft
Input SPK (SA)
|  | Alokasi Mekanik | 1. Saat di Add Mekanik, Detail Data Mekanik tidak ada | uspfn_SvTrnServiceSelectDtl | Bennedict | Done | Bry |  | 2015-01-26 | Benedict | Done
SvTrnServiceMechanicByJobOrderNoView
uspfn_SvTrnGetTaskMechanic
SvTrnServiceMechanicView
|  | Simulasi Harga SPK |  |  | David | Done | Ara | done | 2015-01-28
|  | Pemeliharaan Status SPK |  | SvTrnMaintainSPKView | David | Done | Ara | done | 2015-01-28
|  | Input Pesanan Pekerjaan Luar | 1. Sudah dibuat POT dan mendapatkan Nomor Dokumen, tetapi saat di Browse tidak ada datanya. | SvTrnPOSubConView | Bennedict | Done | Bry |  | 2015-01-26
|  | Input Penerimaan Pekerjaan Luar | 2. Saat di Save, Detail data tidak ada | SvTrnPOSubConRcvView | Bennedict | Done | Bry |  | 2015-01-26
|  | Buat Faktur Penjualan | 1. saat klik proses Receiving muncul Error | uspfn_SvGetFirstBillType | David | Done | Bry |  | 2015-01-26 | David | Done
uspfn_SvTrnInvoiceCreate
uspfn_SvTrnInvoicePosting
uspfn_GnDocumentGetNew
vw_SvTrnInvoiceView
|  | Buat Faktur Penjualan (Batch) |  | uspfn_SvTrnInvInquiryBatch | Yohana | Done | Ara | Belum Bisa ,Saat klik proses invoice yang terjadi hanya loading saja | 2015-01-28
|  | Generate Faktur Pajak Standard |  | uspfn_SvInqFpjStdData | David | Done | Ara
SvTaxInvoiceView
SvCustomerView
|  | Proses Approve PDI/FSC Claim |  |  |  |  | Ara |  | 2015-01-28
|  | Generate Faktur Pajak Gabungan |  |  | David |  | Ara | Saat save muncul warning "internal Error" | 2015-01-28 | David | Done
|  | Generate Faktur Pajak Gabungan (HQ) |  | uspfn_SvInqFpjHQGet | David | Done
SvTaxInvoiceView
SvCustomerView
|  | Maintenance Faktur Penjualan |  | uspfn_SvTrnInvoiceReCalculate | Yohana | Done | Ara | Belum bisa sama sekali, saat klik edit di detail tidak ada yang berpengaruh, tidak sesuai dengan yang desktop karena di aplikasi desktop ada pilihan untuk edit ppn nya | 2015-01-28
uspfn_SvTrnInvUpdPrice
uspfn_SvTrnInvoicePosting
|  | Maintenance Faktur Pajak |  |  | Yohana | Done
|  | Retur Service |  | SvReturnServiceView | Bennedict | Done | Ara | Belum bisa, setelah pilih invoice dan sign nya lalu di save tidak ada yang terproses | 2015-01-28 | Benedict | done | No. Ref harus diisi. Sudah ditambahkan validasi
|  | Cancel Invoice |  | update uspfn_SvTrnInvoiceCancel | Yohana | Done | Ara |  | 2015-01-28
uspfn_RepostingCancelInvoice
Input VOR
| Transaksi - Kupon Service Gratis (KSG) | Get KSG dari SPK |  | uspfn_SvTrnListKsgFromSPK | David | Done
uspfn_GnDocumentGetNew
SvTrnPdiFscView
SvGetAllBranchFromSPKView
|  | Get KSG dari Faktur Penjualan |  | vw_SvTrnInvoiceView | David | Done
Get KSG dari Faktur Penjualan All Branch
|  | Upload Data KSG dari Cabang / Sub-Dealer |  |  | Bennedict | Done
|  | Input KSG |  | SvTrnSenderDealerView | Bennedict | Done
SvTrnPdiFscView
|  | Generate Data KSG dari SPK |  |  | Eko | Done
|  | Generate Data KSG |  |  | Eko | Done
Receive Data KSG
|  | Maintenance KSG |  |  | Eko | Done
| Transkasi - Claim | Input Information Claim (SPK) |  |  | Rudi | Done
|  | Input Information Claim (INV) | di Aplikasi Desktop tidak ada. Hanya menu saja |  | Fery/Rudi | on progress
|  | Input Warranty Claim |  | uspfn_SvGetClaimApp | David/Rudi | Done
|  | Get Claim (SPK/INV) |  | SvTrnClaimView | David/Rudi | Done
|  | Upload Claim Data dari Cabang / Sub-Dealer |  |  | Fery/Rudi | Done
|  | Generate Data Claim |  |  | Fery/Rudi | Done
|  | Receive Claim Data |  | uspfn_SvGetWRcvClaimHdrFile | Rudi | Done
uspfn_SvGetWRcvClaimDtlFile
|  | Maintenance Claim |  |  | Fery/Rudi | Done
| Transaksi - Paket Service | Get Paket Service |  |  | Bennedict | Done
|  | Generate Paket Service |  |  | Bennedict | Done
| Inquiry | Pemantauan Pekerjaan
|  | Surat Perintah Kerja |  | svInqWorkOrder | David | Done
|  | Riwayat Perawatan Kendaraan |  | svInqHistServiceVehicle | David | Done
Riwayat Perawatan Kendaraan (WSDS)
|  | Part & Material |  | svInqPartMaterial | David | Done
|  | Informasi Kendaraan |  | svInqUnitInfo | David | Done
|  | Suzuki MSI |  | svInqMSI | David | Done
Data DCS Service
Pivot Service Transaction
Pivot Service Invoice
Pivot Service Journal
Pivot Customer Vehicle
Pivot Suzuki MSI
Paket Service
| Utility | Upload Data Master
Upload Data from DCS
Posting Laporan
Send Customer Data
Re-Journal & Pembatalan Invoice
Send SMR Data
Maintenance Chassis
Maintenance Service Book No
Reminder SMS
Maintenance Jenis Kendaraan
Birthday SMS
Proses Tutup Bulan
| Laporan - Register | Booking / Estimasi |  |  | Albai | Done
|  | Surat Perintah Kerja |  |  | Albai | Done
|  | Summary Surat Perintah Kerja |  |  | Albai | Done
|  | Pekerjaan Luar |  |  | Albai | Done
|  | Return Part (Cancel Faktur Service) |  |  | Albai | Done
|  | Faktur Service |  |  | Albai | Done
|  | Faktur Service (HQ) |  |  | Albai | Done
|  | Return Service |  |  | Albai | Done
| Laporan - Report | Penjualan Service |  |  | Albai | Done
|  | Penjualan Service Per Kelompok Pekerjaan |  |  | Albai | Done
|  | Penjualan Service Per Model & Pelanggan |  |  | Albai | Done
|  | Penjualan Service Per Periode & Jenis Pekerjaan |  |  | Albai | Done
|  | Penjualan Service Tahunan |  |  | Albai | Done
|  | Penjualan Service Tahunan Per Kelompok Pekerjaan |  |  | Albai | Done
|  | Perbandingan Penjualan Service Tahunan |  |  | Albai | Done
|  | Perincian Insentif |  |  | Albai | Done
|  | Laporan Service Per Mekanik |  |  | Albai | Done
|  | Laporan Customer Aktif / Pasif |  |  | Albai | Done
|  | Laporan Izin Keluar Kendaraan |  |  | Albai | Done
|  | Laporan Body Repair |  |  | Albai | Done
|  | Dokumen Pending |  |  | David | Done
|  | History Kendaraan |  |  | David | Done
Laporan Faktur Penjualan (Pre-Printed)
| Laporan - Service | PDI & FSC Dealer Claim
Claim Detail List
Aktifitas Service by Mekanik & Unit
|  | Kinerja / Performa Service |  |  | David | Done
|  | Review Service Advisor |  |  | David | Done
FSC Campaign List
| SRS | Service Reminder
Data Retensi Harian (DRH)
Daily SMS

## Finance
MODULE | MENU | PROGRAM | STORE PROCEDURE / FUNCTION / VIEW | DEVELOPER |  | QC |  | FIXING
|  |  |  | PIC | STATUS | PIC | STATUS | PIC | STATUS | COMMENT

## Tax
MODULE | MENU | PROGRAM | STORE PROCEDURE / FUNCTION / VIEW | DEVELOPER |  | QC |  | FIXING
|  |  |  | PIC | STATUS | PIC | STATUS | PIC | STATUS | COMMENT
TAX | Pajak | Generate Faktur Pajak
Generate Faktur Pajak (Online)
|  | Konsolidasi Pajak Masukan |  | David | On Progress
Konsolidasi Pajak Keluaran
Entry Pajak Manual
|  | Maintenance Faktur Pajak Standard |  | Rijal | Done
| Cetak Form | Faktur Pajak
| Laporan | Pajak Masukan |  | Rijal | Done
|  | Pajak Keluaran |  | Rijal | Done
|  | Akumulasi PPN yang harus dibayar |  | Syawal | Done
|  | PPN yang harus dibayar per Periode |  | Syawal | Done
|  | Laporan Pajak Masukan eSPT 1111 |  | Rijal | Done
|  | Laporan Pajak Keluaran eSPT 1111 |  | Rijal | Done
| Utility | Setting Faktur Pajak
Perbaikan Nomor Pajak